## Template
EDCI 573 Practicum Project Plan | [6 empty] | PROJECT SCHEDULE
[7 empty] | 2014-01-12 | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02
| STATUS | % DONE | DELIVERABLES/COMPONENTS/ACTIVITIES | WORK HOURS | DURATION | WHO | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8

## Example
EDCI 573 Practicum Project Plan | [6 empty] | 2014-01-12 |  | 2014-01-19 | 2014-01-26 | 2014-02-02 | 2014-02-09 | 2014-02-16 | 2014-02-23 | 2014-03-02
| STATUS | % DONE | DELIVERABLES/COMPONENTS/ACTIVITIES | WORK HOURS | DURATION | WHO | Week 1 |  | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
1. Analysis
| OT | 100% | 1.1 Survey of Learners | 3 hours | 5 days | LDT student
| OT | 100% | 1.2 Content Analysis (comparison of current content and standards | 4 hours | 3 days | LDT student & SME Team
| OT | 100% | 1.3 Identification of new objectives | 1 hour | 2 days | LDT Student
2. Design
| OT | 100% | 2.1 Creation of a Curriculum Blueprint for the Learning Modules | 4 hours | 5 days | LDT Student
| OT | 100% | 2.2 Three sample designs for new curriculum | 2 hours | 2 days | LDT Student
| OT | 100% | 2.3 Selection of final design choice | 1 hour | 3 days | LDT Student, SME Team, & Client
3. Development
| AR | 25% | 3.1 Creation of Module 1 | 15 hours | 8 days | LDT Student
| ID | 0% | 3.1.1 Intro Video and Job Aid | 3 hours | 4 days | LDT Student and Intern (provided by client for video support)
| AR | 25% | 3.1.2 Interactive Quiz | 3 hours | 4 days | LDT Student
| AR | 0% | 3.1.3 Review of Content Accuracy | 2 hours | 2 days | LDT student & SME Team
|  | 0% | 3.2 Creation of Module 2 | 15 hours | 8 days | LDT Student
|  | 0% | 3.2.1 Intro Video and Job Aid | 3 hours | 4 days | LDT Student and Intern (provided by client for video support)
|  | 0% | 3.2.2 Interactive Quiz | 3 hours | 4 days | LDT Student
|  | 0% | 3.2.3 Review of Content Accuracy | 2 hours | 2 days | LDT student & SME Team
4. Implementation
|  | 0% | 4.1 Pilot Module 1 and 2 | 2 hours | 1 day | LDT Student & Pilot Learner Group
5. Evaluation
|  | 0% | 5.1 Collect and Analyze Learner Performance Data | 3 hours | 2 days | LDT student & SME Team
|  | 0% | 5.2 Collect and Analyze Learner Survey Data | 4 hours | 6 days | LDT Student
|  | 0% | 5.3 Create Revision Recommendation Report | 6 hours | 3 days | LDT Student
|  | 0% | 5.4 Present Revision Recommendation Report | 2 hours | 1 day | LDT Student, SME Team, & Client
EDCI 573 Major Project Deadlines
[8 empty] | 573: Pre-Proposal Due |  | 573: Proposal Due |  | 573: Artifact 1 Due |  | 573: Artifact 2 Due | 573: Final Project Report Due
|  | OT | On Target
|  | NS-PP | Not Started but On Target Pending Progress of Project
|  | AR | At Risk
|  | ID | In Danger
Reminder: 573 Projects are due by Sunday, midnight EST at the start of the week unless otherwise noted. Check Course Schedule for exact due dates.
Note on D2: Tim Newby: This is given as an example, the titles of the Deliverables in your Project Plan should contain actual names of those deliverables/components, etc.
Note on G2: Tim Newby: For your actual plan, these should be names of you and the people who have this responsibility.